## WBS with Gantt Chart BLANK
Gantt Chart
Project Title | UniLib - University Library Management System
Project Manager | Nguyễn Phan Thế Vinh
Company Name | 2 girls 2 cúp (Team ID: T05)
Date | 15/10/2026
WBS Number | Task Title | Task Owner | Start Date | Due Date | Duration | % of Task Complete | WeeK 1 | [6 empty] | WeeK 2 | [6 empty] | WeeK 3 | [6 empty] | WeeK 4 | [6 empty] | WeeK 5 | [6 empty] | WeeK 6 | [6 empty] | WeeK 7 | [6 empty] | WeeK 8 | [6 empty] | WeeK 9 | [6 empty] | WeeK 10 | [6 empty] | WeeK 11 | [6 empty] | WeeK 12
[7 empty] | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4 | T5 | T6 | T7 | CN | T2 | T3 | T4
1 | PA1 Initiation & Planning | Vinh | 15/10/2026 | 21/10/2026 | 6 | 100%
1.1.1 | Project Kickoff Meeting & Charter Sign-off | Vinh | 15/10/2026 | 15/10/2026 | 0 | 100%
1.1.2 | Governance & Roles Alignment | Vinh | 15/10/2026 | 16/10/2026 | 1 | 100%
1.2.1 | Preliminary Vision & Problem Statement | Nguyên | 16/10/2026 | 18/10/2026 | 2 | 100%
1.2.2 | Stakeholder Needs & MoSCoW Scope | Nguyên | 17/10/2026 | 19/10/2026 | 2 | 100%
1.2.3 | Preliminary Architecture & Technology Justification | Ánh | 16/10/2026 | 18/10/2026 | 2 | 100%
1.2.4 | Hardware & Operating Environment Specification | Ánh | 17/10/2026 | 19/10/2026 | 2 | 100%
1.2.5 | Process Gates & Exit Criteria Definition | Vinh | 16/10/2026 | 17/10/2026 | 1 | 100%
1.2.6 | Work Breakdown Structure (WBS) Authoring | Vinh | 17/10/2026 | 19/10/2026 | 2 | 100%
1.2.7 | Effort & Cost Estimation Baseline | Vinh | 18/10/2026 | 20/10/2026 | 2 | 100%
1.2.8 | Project Schedule & Critical Path Mapping | Ánh | 18/10/2026 | 20/10/2026 | 2 | 100%
1.2.9 | Project Risk Identification & Mitigation | Vinh | 19/10/2026 | 20/10/2026 | 1 | 100%
1.3.1 | Version Control & Repository Structure Setup | Quân | 16/10/2026 | 17/10/2026 | 1 | 100%
1.3.2 | Task Board & Tracking Configuration | Quân | 18/10/2026 | 20/10/2026 | 2 | 100%
1.3.3 | PA1 Document Compilation & Review | Vinh | 20/10/2026 | 21/10/2026 | 1 | 100%
2 | PA2 Requirements Engineering | Nguyên | 22/10/2026 | 04/11/2026 | 13 | 0%
2.1.1 | Domain Modeling & Glossary Definition | Nguyên | 22/10/2026 | 24/10/2026 | 2 | 0%
2.1.2 | System Use Case Modeling | Nguyên | 24/10/2026 | 27/10/2026 | 3 | 0%
2.2.1 | F01 User Authentication & Roles Specification | Nguyên | 27/10/2026 | 30/10/2026 | 3 | 0%
2.2.2 | F02 Book Catalog Management Specification | Nguyên | 27/10/2026 | 30/10/2026 | 3 | 0%
2.2.3 | F03 Book Copy Management Specification | Nguyên | 28/10/2026 | 31/10/2026 | 3 | 0%
2.2.4 | F04 Search & Browse Specification | Nguyên | 28/10/2026 | 31/10/2026 | 3 | 0%
2.2.5 | F05 Borrow & Return Management Specification | Nguyên | 29/10/2026 | 01/11/2026 | 3 | 0%
2.2.6 | F06 Book Reservation Specification | Nguyên | 30/10/2026 | 02/11/2026 | 3 | 0%
2.2.7 | Non-Functional Requirements & Constraints | Ánh | 29/10/2026 | 01/11/2026 | 3 | 0%
2.3.1 | Reader/Student Workflow Wireframes | Ánh | 30/10/2026 | 02/11/2026 | 3 | 0%
2.3.2 | Librarian & Admin Management Wireframes | Ánh | 30/10/2026 | 02/11/2026 | 3 | 0%
2.4.1 | Requirements Traceability Matrix (RTM) Baseline | Vinh | 01/11/2026 | 03/11/2026 | 2 | 0%
2.4.2 | PA2 Document Review & Verification | Vinh | 02/11/2026 | 04/11/2026 | 2 | 0%
3 | PA3 Architecture & Detailed Design | Ánh | 05/11/2026 | 18/11/2026 | 13 | 0%
3.1.1 | C4 Architecture Modeling (Context & Container) | Ánh | 05/11/2026 | 08/11/2026 | 3 | 0%
3.1.2 | Architectural Decision Records (ADRs) | Quân | 07/11/2026 | 10/11/2026 | 3 | 0%
3.2.1 | Conceptual & Logical Data Modeling (ERD) | Ánh | 07/11/2026 | 10/11/2026 | 3 | 0%
3.2.2 | Physical Database Schema & DDL Scripts | Quân | 10/11/2026 | 13/11/2026 | 3 | 0%
3.3.1 | API Specification for F01 Auth & User Management | Quân | 10/11/2026 | 13/11/2026 | 3 | 0%
3.3.2 | API Specification for F02 Catalog & F03 Copy Management | Quân | 11/11/2026 | 14/11/2026 | 3 | 0%
3.3.3 | API Specification for F04 Search & Browse | Quân | 12/11/2026 | 15/11/2026 | 3 | 0%
3.3.4 | API Specification for F05 Borrow & Return | Quân | 12/11/2026 | 15/11/2026 | 3 | 0%
3.3.5 | API Specification for F06 Book Reservation | Quân | 13/11/2026 | 16/11/2026 | 3 | 0%
3.4.1 | UI Design System & Component Library | Ánh | 08/11/2026 | 12/11/2026 | 4 | 0%
3.4.2 | High-Fidelity Mockups for Key Workflows | Ánh | 12/11/2026 | 16/11/2026 | 4 | 0%
3.5.1 | Design Review & Traceability Verification | Vinh | 15/11/2026 | 18/11/2026 | 3 | 0%
4 | PA4 Test Planning & QA Setup | Vinh | 19/11/2026 | 25/11/2026 | 6 | 0%
4.1.1 | Master Test Plan Authoring | Vinh | 19/11/2026 | 21/11/2026 | 2 | 0%
4.1.2 | Test Automation Framework Setup | Quân | 19/11/2026 | 22/11/2026 | 3 | 0%
4.2.1 | Test Cases for F01 Authentication & Roles | Vinh | 20/11/2026 | 22/11/2026 | 2 | 0%
4.2.2 | Test Cases for F02 Catalog & F03 Copy Management | Vinh | 20/11/2026 | 22/11/2026 | 2 | 0%
4.2.3 | Test Cases for F04 Search & Browse | Vinh | 21/11/2026 | 23/11/2026 | 2 | 0%
4.2.4 | Test Cases for F05 Borrow & Return | Vinh | 21/11/2026 | 23/11/2026 | 2 | 0%
4.2.5 | Test Cases for F06 Book Reservation | Vinh | 22/11/2026 | 24/11/2026 | 2 | 0%
4.3.1 | Test Traceability Matrix & Test Data Specification | Nguyên | 22/11/2026 | 24/11/2026 | 2 | 0%
4.3.2 | PA4 Document Review & Baseline | Vinh | 23/11/2026 | 25/11/2026 | 2 | 0%
5 | PA5 Implementation, Testing & Deployment | Quân | 26/11/2026 | 09/12/2026 | 13 | 0
5.1.1 | Backend Boilerplate & DB Connection Setup | Quân | 26/11/2026 | 28/11/2026 | 2 | 0%
5.1.2 | Frontend Boilerplate & Layout Setup | Quân | 26/11/2026 | 28/11/2026 | 2 | 0%
5.2.1 | F01 Authentication & Role-Based Access Control | Quân | 27/11/2026 | 29/11/2026 | 2 | 0%
5.2.2 | F02 Book Catalog Management Module | Quân | 28/11/2026 | 01/12/2026 | 3 | 0%
5.2.3 | F03 Book Copy Management Module | Quân | 29/11/2026 | 02/12/2026 | 3 | 0%
5.2.4 | F04 Search & Browse Books Module | Ánh | 30/11/2026 | 03/12/2026 | 3 | 0%
5.2.5 | F05 Borrow & Return Management Module | Quân | 01/12/2026 | 04/12/2026 | 3 | 0%
5.2.6 | F06 Book Reservation Module | Quân | 02/12/2026 | 05/12/2026 | 3 | 0%
5.2.7 | Reader Dashboard & Active Loans View | Ánh | 03/12/2026 | 05/12/2026 | 2 | 0%
5.3.1 | Automated Unit & Integration Testing | Quân | 03/12/2026 | 06/12/2026 | 3 | 0%
5.3.2 | Manual System Testing & Bug Logging | Vinh | 04/12/2026 | 07/12/2026 | 3 | 0%
5.3.3 | Bug Fixing & Regression Verification | Quân | 05/12/2026 | 08/12/2026 | 3 | 0%
5.3.4 | Test Summary Report & QA Sign-off | Vinh | 07/12/2026 | 09/12/2026 | 2 | 0%
5.4.1 | Cloud DB & Backend Deployment on Render | Quân | 06/12/2026 | 08/12/2026 | 2 | 0%
5.4.2 | Frontend Cloud Deployment on Vercel | Quân | 06/12/2026 | 08/12/2026 | 2 | 0%
5.4.3 | Production Smoke Testing & Deployment Documentation | Vinh | 07/12/2026 | 09/12/2026 | 2 | 0%
5.4.4 | PA5 Submission & Code Baseline | Vinh | 08/12/2026 | 09/12/2026 | 1 | 0%
6 | Final Presentation, Demo & Closeout | Vinh | 10/12/2026 | 16/12/2026 | 6 | 0%
6.1.1 | Demo Scenario Scripting & Seed Data Preparation | Nguyên | 10/12/2026 | 12/12/2026 | 2 | 0%
6.1.2 | Demo Rehearsal & Backup Recording | Vinh | 12/12/2026 | 14/12/2026 | 2 | 0%
6.2.1 | Presentation Slide Deck Creation | Ánh | 11/12/2026 | 14/12/2026 | 3 | 0%
6.2.2 | Final Contribution Assessment & Project Retrospective | Vinh | 14/12/2026 | 16/12/2026 | 2 | 0%
END SHEET